## SWARM
SWARM ROBOTICS
Starting Date | [7 empty] | 2020-11-25
Expected Tasks Completion Date | [7 empty] | 2021-01-30
Sl. No. | Section | Tasks | Ex.Date | Revised date of Completion | Actual Completion Date | Status | Team Member | Comments
1 | PHASE 0 | *Particle Swarm Optimization | 2020-11-25 |  |  |  | Akhil P Jacob | Software and Research
[7 empty] | Anu Antony | Software and Research
|  | *Ant System Algorithm | 2020-11-26 |  |  |  | Sooraj/Jerin | Hardware and Electronic Support
|  | *Ant Colony System Algorithm | 2020-11-27
|  | *Bees Algorithm | 2020-11-28
|  | *Bacterial foraging Algorithm | 2020-11-30
|  | *Coordinate Geometry | 2020-12-03
|  | *Vector Algebra | 2020-12-10
|  | *Conic Sections | 2020-12-12
|  | *Pygame | 2020-12-14
2 | PHASE 1 | *Creating 4 Autonomous Self aware bots | 2020-12-16
|  | *Create Localization Technology without | 2020-12-24
using obstacles in robots using QR code
and Coordinate Robo Guidance System
|  | *Pattern Formation | 2021-01-08
|  | *Feedback system collective Intelligence | 2021-01-23
Software
|  | *Testing,Bug Fixing,PCB designing | 2021-01-30